## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Machine Learning
INTERN NAME: | Vicky Vilas Pukale
PROJECT NAME: | Career Path Prediction and Guidance System
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 30-Jun-2026
Purpose of Document
This Lessons Learnt Log has been prepared as part of the Career Path Predictor project, developed under the Industry Academia Community programme. The project involved building a machine learning-based web application that predicts the most suitable tech job role for a user based on their skills, interests, and personal traits, using an ensemble of four models — Random Forest, XGBoost, LightGBM, and CatBoost — trained on the PS2 career survey dataset. This document captures key lessons encountered during data preprocessing, model training, feature engineering, UI development, and deployment, with the aim of helping future interns and project teams avoid similar challenges and adopt better practices from the outset.
The insights recorded here reflect real events observed across the project lifecycle, covering areas such as data quality issues, model integration challenges, environment compatibility problems, and user experience gaps. Each lesson includes early warning signs, recommendations, and the actions taken, serving as a practical reference for anyone working on similar ML-powered application projects within the Industry Academia Community.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Career Path Prediction and Guidance System |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID | ML-PROJ-2025-01
PROJECT MANAGER | Harshada Topale
PROJECT SPONSOR | Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 02-Jun-2026 | All 5 trained models (4 ML + 1 DL) scored close to random-guess accuracy on the held-out test set. | Data Quality | Yes | Run a mutual-information check between features and target before investing further time in model tuning. | Performed mutual-information analysis; confirmed the dataset carries very little real signal for this target; documented the limitation transparently instead of over-fitting to noise. | Intern (Vicky Vilas Pukale) | Solved | Kept the full pipeline production-shaped so it will work correctly on a dataset with real signal.
2 | 28-May-2026 | TensorFlow full install was very large and slow to download in the sandboxed environment. | Technical/Environment | No | Prefer the lighter tensorflow-cpu package and allow extra timeout for first-time installs. | Installed tensorflow-cpu with an increased pip timeout instead of the full GPU-enabled tensorflow package. | Intern (Vicky Vilas Pukale) | Solved | No further issues after switching packages.
3 | 05-Jun-2026 | Initial column-name mismatch (trailing whitespace) caused a KeyError during preprocessing. | Technical/Development | No | Always strip column names right after reading a CSV, and keep string constants consistent with the stripped names. | Standardized column-name stripping in load_raw_data() and fixed the mismatched constant. | Intern (Vicky Vilas Pukale) | Solved | A simple utility fix; worth checking column names for hidden whitespace on any new dataset.
4 | 20-Jun-2026 | Ensuring the Streamlit app used the exact same encoders/scaler as training required care. | Process | Yes | Persist all preprocessing artifacts (encoders, scaler, feature column order) to disk during training and load them, unchanged, in the app. | Centralized preprocessing logic in a shared preprocessing.py module imported by both train.py and app.py. | Intern (Vicky Vilas Pukale) | Solved | This pattern should be reused in future ML projects to avoid train/serve skew.
5 | 29-Jun-2026 | Documentation (SRS, Project Charter, RAID log, etc.) took longer than expected to complete thoroughly. | Planning | Yes | Start documentation in parallel with development rather than only at project closure. | Drafted documentation templates early and filled them incrementally as project decisions were made. | Intern (Vicky Vilas Pukale) | Solved | Recommend allocating explicit schedule time for documentation in future project plans.