## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Career Path Prediction and Guidance System
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 26-May-2026
EXPECTED COMPLETION DATE | 30-Jun-2026
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To build a Deep Learning / Machine Learning based system that evaluates a student's academic performance, skills, and interests to recommend the most suitable career path(s) and suggest relevant courses to help them reach that career goal.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | Students often choose a specialization or career track without a clear, objective view of how their existing skills, academic performance and interests align with real job roles. Cloud Counselage wants a data-driven guidance tool that removes this guesswork, helping students make informed academic and career decisions early, which in turn improves student outcomes and overall workforce productivity.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Achieve a working end-to-end prediction pipeline (data preprocessing, EDA, model training, evaluation) covering at least 4 ML models and 1 DL model, and deploy the best model in a Streamlit web app within the 5-week internship duration (26-May-2026 to 30-Jun-2026).
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | 1) Cleaned & preprocessed dataset with saved encoders/scaler. 2) EDA report with visualizations. 3) Trained ML models (Logistic Regression, Random Forest, SVM, XGBoost) and one DL model (Keras MLP). 4) Model evaluation report (accuracy, precision, recall, F1). 5) A Streamlit web application where a student can input their profile and receive a predicted career path with recommended courses. 6) Complete project documentation (SRS, WBS, Project Schedule, RAID log, Lessons Learnt Log, Project Report).
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | Data cleaning & preprocessing, exploratory data analysis, training/evaluating ML & DL models on the provided dataset, saving the best-performing model, and building a Streamlit UI that takes student inputs and returns a predicted career + recommended courses.
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | Integration with live college/university student databases, real-time data collection from students, mobile app version, multi-language support, and authentication/user-account management.
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | 1 Intern (Vicky Vilas Pukale) with guidance from assigned Project Manager/Mentor.
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Laptop with Python 3.x, internet access, GitHub/Streamlit Community Cloud account for deployment.
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | N.A. (Internship project - no monetary cost; resource cost is intern's time - approx. 5 weeks, part-time effort).
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Cloud Counselage Pvt. Ltd. (Industry Academia Community - IAC GPI Program)
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Project Sponsor, Project Manager, Assigned Intern (Vicky Vilas Pukale), IAC Program Coordinators.
END CUSTOMER (Mention the client name.) | Cloud Counselage Pvt. Ltd. / Students who will use the career guidance tool.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | Dataset may have weak/no statistical relationship between features and target career labels, leading to low model accuracy; limited time (5 weeks) to explore advanced feature engineering; intern's limited prior exposure to Deep Learning frameworks may slow development.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | The provided dataset (PS2_Dataset.csv) is representative of real student profiles; Streamlit Community Cloud / local hosting is an acceptable deployment target; the intern will have consistent access to a laptop and internet for the full internship duration.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | 5-week internship timeline (26-May-2026 to 30-Jun-2026); single intern resource; no budget for paid compute/cloud resources; must use free/open-source tools (Python, scikit-learn, TensorFlow, Streamlit).
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | 01-Jun-2026
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | 05-Jun-2026
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | 12-Jun-2026
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | 22-Jun-2026
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | 25-Jun-2026
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | 28-Jun-2026
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | 30-Jun-2026