## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 3 | 0 | 1 | 1 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Career Path Prediction & Guidance System |  | Project Id: | IAC-GPI-2026-CPP | Project Manager: | Harshada Topale |  |  | Assumption | 2 | 0 | 0 | 0 | 1 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2026-06-30 | Project Team Lead: | Vicky Pukale |  |  | Dependency | 2 | 0 | 0 | 0 | 1 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 9 |  |  |  |  | 4
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Dataset may show little to no statistical relationship between input features and the target career label. | Model accuracy could remain close to random-guess baseline, weakening the usefulness of predictions. | Run a mutual-information/feature-importance check early; document findings transparently; treat the app as a working pipeline demo if data signal is weak. | Intern (Vicky Vilas Pukale) | High | 15 | Open | Risk
2 | Risk | Limited 5-week timeline may not allow for extensive hyperparameter tuning. | Final model performance may be sub-optimal. | Prioritize a working end-to-end pipeline first, then use any remaining time for tuning. | Intern (Vicky Vilas Pukale) | Moderate | 10 | Open | Assumption
3 | Risk | Intern has limited prior hands-on experience with TensorFlow/Keras. | Development of the Deep Learning model could take longer than planned. | Allocate extra buffer time in the schedule for the DL model and refer to official TensorFlow documentation/tutorials. | Intern (Vicky Vilas Pukale) | Moderate | 10 | Closed | Issue
4 | Assumption | The provided PS2_Dataset.csv is assumed to be representative enough for training a demo model. | If untrue, model outputs may not generalize to real students. | Clearly document this assumption and its impact on prediction reliability in the final report. | Project Manager | Low |  | Open | Dependency
5 | Assumption | Streamlit Community Cloud (or local hosting) is an acceptable deployment target for this internship. | No impact expected; if untrue, deployment approach would need to change. | Confirm deployment expectations with Project Manager at project kickoff. | Project Manager | Negligible |  | Closed
6 | Issue | Initial model training run showed near-random accuracy (~8-10%) across all models. | Risk of the deliverable being perceived as non-functional if not explained. | Performed mutual-information analysis to confirm the issue was data-related, not a pipeline bug; documented clearly in README/Project Report. | Intern (Vicky Vilas Pukale) | High |  | Closed | Open
7 | Issue | TensorFlow package installation took longer than expected due to package size. | Minor delay in starting Deep Learning model development. | Installed tensorflow-cpu (lighter build) with extended timeout; verified installation before proceeding. | Intern (Vicky Vilas Pukale) | Low |  | Closed | Closed
8 | Dependency | Streamlit app depends on the encoders.pkl and scaler.pkl artifacts produced by the training script. | If training artifacts are missing/out of sync, the app will fail to load or produce incorrect predictions. | Always re-run train.py after any change to preprocessing.py before launching the app; keep artifacts version-controlled together. | Intern (Vicky Vilas Pukale) | Moderate |  | Closed
9 | Dependency | Final project documentation depends on the training/evaluation results being finalized. | Any change to the best model after documentation is written would need a re-check of the report. | Freeze the model choice before writing the final Project Report and Lessons Learnt Log. | Intern (Vicky Vilas Pukale) | Low |  | Open | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24